## Slide 1
WEEK 4 PROGRESS UPDATE
Capstone Project
Progress Update
Design and Evaluation of a Deception-in-Depth
Honeynet Architecture for Observing Multi-Stage Attacker Behaviour
Mentor
Dr. Ho Chen
Team Members
4 Students
Timeline
Week 4 of 12

## Slide 2
MEETING AGENDA
What We'll Cover Today
01
Project Overview
Research objectives, questions, and hypothesis
02
Completed Milestones
Week 1-4 deliverables and achievements
03
Progress Summary
Metrics, timeline status, and completion rate
04
Technical Architecture
Three-layer deception system design
05
Upcoming Milestones
Week 5-12 plan and deadlines
06
Risk Assessment
Key risks and mitigation strategies

## Slide 3
PROJECT OVERVIEW
What We're Building
Primary Objective
Design, implement, and evaluate a layered Deception-in-Depth honeynet architecture capable of observing multi-stage attacker behaviour across network, host, and data layers.
Experimental Approach
Deploy a controlled virtual environment on Proxmox VE with 5-6 VMs simulating a small enterprise network. Observe attacker interactions and measure behavioural impact using three key metrics.
Key Behavioural Metrics
01
Misdirection
Decoy interactions
02
Delay
Time spent
03
Engagement
Depth reached
Three Deception Layers
Layer 1
Network
T-Pot CE honeypot services (SSH, HTTP, SMB)
Layer 2
Host
GOAD Active Directory + Windows enterprise hosts
Layer 3
Data
HoneyLambda + decoy S3 cloud credentials
Deception Control Plane: Staged activation based on attacker actions

## Slide 4
RESEARCH FRAMEWORK
Research Questions & Hypothesis
RQ1
Attacker Navigation
How does layered deception influence attacker navigation within the honeynet?
RQ2
Decision Influence
To what extent do deception artifacts influence attacker decisions?
RQ3
Engagement Depth
Does staged activation of deception layers increase engagement?
RQ4
Time Impact
How does layered deception affect time attackers spend interacting?
RQ5
Activity Patterns
What activities are observed across different attack lifecycle stages?
Central Hypothesis
A staged Deception-in-Depth architecture will encourage attackers to interact more extensively with deceptive assets and explore more layers than a single-layer honeypot.
Increase engagement depth across multiple hosts
Influence attacker navigation through artifacts
Introduce delays in attacker progression
MITRE ATT&CK Mapping
Observed activities mapped to structured tactics:
Reconnaissance
Credential Access
Lateral Movement
Collection
Exfiltration

## Slide 5
TECHNICAL DESIGN
Three-Layer Deception Architecture
L1
Network
Initial Access
Components
• T-Pot CE platform
• SSH, HTTP, SMB services
• Simulated subnets
MITRE ATT&CK
Reconnaissance
Credential Access
Expected Behaviour
Scanning, credential brute force
L2
Host
Lateral Movement
Components
• GOAD Active Directory
• Windows clients & servers
• Domain controller
MITRE ATT&CK
Privilege Escalation
Lateral Movement
Expected Behaviour
Enumeration, credential harvesting
L3
Data/Cloud
Exfiltration
Components
• HoneyLambda
• Decoy S3 buckets
• Fake API keys
MITRE ATT&CK
Collection
Exfiltration
Expected Behaviour
Credential reuse, cloud enumeration
Telemetry Flow
All layers → LOG01 (centralized monitoring) → Normalization → Structured datasets → Behavioural analysis
Deception Control Plane
Conditional layer activation based on attacker triggers: login success → command execution → credential interaction

## Slide 6
COMPLETED MILESTONE
Milestone 1: Literature Review
Key Research Findings
COMPLETED
Landsborough et al. (2024)
Deception-in-Depth strategy with three logical layers (network, host, data). Single-layer deception may be insufficient as attackers can detect isolated honeypots.
Gaddam (2025)
Deception techniques increase attacker effort and improve visibility into attacker behaviour patterns.
Fraunholz et al. (2021)
Adaptive deployment and dynamic configuration are crucial for responding to attacker activity in honeynet systems.
Research Gap Identified
Despite advances in cyber deception, there remains a gap in experimentally evaluating how layered deception influences attacker behaviour across multiple stages within controlled and reproducible environments.
Milestone Details
Timeline
Week 1-2
Learning Hours
30
Status
Complete
Key Concepts Covered
Encouraging vs. discouraging deception
Multi-layered deception architectures
Attacker behaviour influence
Honeynet deployment strategies
Controlled experimentation
Completed
Week 2

## Slide 7
COMPLETED MILESTONE
Milestone 2: Architecture Design
System Architecture Overview
COMPLETED
L1
Network Deception Layer
T-Pot CE platform with SSH, HTTP, SMB services
T-Pot CE
SSH
HTTP
L2
Host Deception Layer
GOAD Active Directory + Windows enterprise hosts
GOAD
AD
Windows
L3
Data Deception Layer
HoneyLambda + decoy S3 buckets with fake API keys
HoneyLambda
S3
API Keys
Deception Control Plane
Conditional activation system that exposes deeper layers based on attacker actions (login success, command execution, credential interaction).
Milestone Details
Timeline
Week 3
Learning Hours
25
Status
Complete
5-VM Deployment Layout
LOG01
4GB RAM
TPOT01
8GB RAM
DC01
6GB RAM
WS01
4GB RAM
FS01
4GB RAM
Total RAM
26 GB
Completed
Week 3

## Slide 8
PROGRESS OVERVIEW
30% Complete — On Track
3/10
Milestones
Completed
80/300
Learning Hours
Invested (26.7%)
4/12
Weeks
Elapsed (33.3%)
Project Timeline Progress
Completion Status
Overall Progress
30%
Time Elapsed
33.3%
Hours Invested
26.7%
Key Achievements
Literature review completed with key findings
Three-layer architecture designed
Proxmox environment operational
5 VMs deployed and configured
Network segmentation established
On Schedule
All deliverables met on time

## Slide 9
COMPLETED MILESTONE
Milestone 3: Proxmox Environment Setup
Deployment Platform
COMPLETED
32 GB
Total RAM
SSD
Storage
Platform
Proxmox VE
Deployment Model
Isolated Virtual Lab
Reset Mechanism
Snapshots & Rollback
Network Segmentation
NET-EXT
External
Attacker-facing services (TPOT01)
NET-INT
Internal
Enterprise network (DC01, WS01, FS01)
NET-MGMT
Management
Admin & logging (LOG01)
Milestone Details
Timeline
Week 4
Learning Hours
25
Status
Complete
5 Core VMs Deployed
LOG01
Monitoring & Logging
TPOT01
Network Honeypot
DC01
Domain Controller
WS01
Workstation
FS01
File Server
Completed
Week 4

## Slide 10
UPCOMING WORK
Milestones: Week 5–7
WEEK
5
Milestone 4: Network Honeypot Deployment
UPCOMING
Learning Hours
35
Primary Tool
T-Pot CE
Focus
Service Config
SSH honeypot
Web honeypot
Banner tuning
Credential seeding
WEEK
6-7
Milestone 5: Host-Level Environment Setup
UPCOMING
Learning Hours
45
Primary Tool
GOAD
Focus
AD + Hosts
Active Directory
Domain controller
Workstation setup
Decoy accounts
WEEK
8
Milestone 6: Deception Artifact Implementation
UPCOMING
Learning Hours
25
Focus
Artifacts
Scope
All Layers
Fake credentials
Decoy documents
API keys
Cloud references

## Slide 11
UPCOMING WORK
Milestones: Week 9–12
W9
Milestone 7
Telemetry Pipeline
UPCOMING
Hours
30
Output
Structured Logs
W10
Milestone 8
Experiment Execution
UPCOMING
Hours
30
Scenarios
A, B, C
W11
Milestone 9
Behavioural Analysis
UPCOMING
Hours
30
Output
Metrics + Paths
W12
Milestone 10
Final Report
UPCOMING
Hours
25
Output
Capstone Report
Complete Project Timeline

## Slide 12
RISK MANAGEMENT
Risk Assessment & Mitigation
RAM Pressure Risk
Running multiple VMs simultaneously may exceed 32GB capacity
Mitigation
• Use 5-VM baseline (26GB)
• Defer optional VM6 (ADM01)
• Monitor resource usage
AD Lab Complexity
Domain-based environments can be difficult to build manually
Mitigation
• Use GOAD as base template
• Limit modifications to deception
• Document configuration steps
Logging Scope Management
Centralized telemetry can become overwhelming if scope is too broad
Mitigation
• Collect only metrics-relevant logs
• Focus on 3 behavioural indicators
• Use lightweight processing
Experiment Reproducibility
Without reset capability, repeated tests may become inconsistent
Mitigation
• Proxmox snapshots as core workflow
• Clean + experiment-ready states
• Documented reset procedures
All Risks Manageable
Mitigation strategies in place. Project remains feasible within capstone timeframe and resource constraints.

## Slide 13
PROJECT STATUS: ON TRACK
Next Steps & Questions
Immediate Next Step
Begin Milestone 4: Network Honeypot Deployment in Week 5
T-Pot CE configuration, service banner tuning, credential seeding (35 hours)
30%
Complete
8
Weeks Remaining
220
Hours Planned
Project on track for Week 12 completion
All milestones achievable within allocated learning hours and timeline
Thank You
Open for feedback and questions